## Flowchart
DRAFT RRAMP FLOWCHART
Wajon & Associates

## Road
1. DESCRIBE ROAD ENVIRONMENT |  |  |  | 2. IDENTIFY NEEDS FOR ROADWORK
Complete table below to collect information of the road and associated infrasstructure |  |  |  | Click on the cells in Column H to select the condition of each factor. Complete onle 1 table
SEALED ROAD
ROAD ENVIRONMENT | DATA |  | DATA SOURCE | FACTOR | SELECT CONDITION (DROP LIST) | SCORE | Traffic | Hazard density
1. LOCATION AND EXTENT |  |  |  | Traffic flow |  |  | <800 | Hazard within 3 metres; Crash severity high
a) Location |  |  |  | Roadside Hazards |  |  | 800-1,000 | Hazard 3-6 metres; Crash severity high
b) Extent |  |  |  | Terrain | Flat | 1 | 1,000-2,500 | Hazard within 3 metres; Crash severity moderate
2. ASSET OWNERSHIP AND STATUS |  |  |  | Design speed relationship to zoned speed |  |  | >2,500 | Hazard 3-6 metres; Crash severity moderate
a) Ownership |  |  | Roman database | Sight Distance | Compliant | 0 |  | Hazard within 3 metres; Crash severity slight
i) Private road |  |  |  | Deficiency in Vertical Geometry |  |  | Speed | Hazard 3-6 metres; Crash severity slight
ii) Local Gov road |  |  |  | Deficiency in Horizontal Geometry |  |  | 10km/h above zoned speed
iii) State Gov road |  |  |  | Number of lanes | Adequate | 0 | Equals zoned speed
iv) Federal Gov road |  |  |  | Lane width |  |  | 10km/h below zoned speed
v) Other |  |  |  | Sealed shoulder width |  |  | 20km/h below zoned speed
b) Status |  |  |  | Seal condition | Good condition | 1 |  | Gravel
i) Structure and Condition | [5 empty] | 2 | Geometry | Not applicable
- Seal width |  |  | Site measurement | Sealed Road Hazard Score |  | 0 | Fully compliant | > 10.0 metres
- Pavement width |  |  | Site measurement |  |  |  | Largely compliant | 7.0 - 10.0 metres
- Formation width |  |  | Site measurement | OR |  |  | Partly compliant | < 7.0 metres
3. TRAFFIC
a) Volume (number) |  |  |  | UNSEALED ROAD |  |  | Lane width
- Current |  |  | Site measure / estimate | FACTOR | SELECT CONDITION (DROP LIST) | SCORE | >3.5 metres | Seal
- Future/ Foreseen |  |  | Estimate | Traffic flow |  |  | 3.0-3.5 metres | Not applicable
b) Traffic Type | % | No. |  | Roadside Hazards |  |  | <3.0 metres | Adequate
i) Current |  |  |  | Terrain |  |  |  | Inadequate
- Local/ passenger |  |  | Site measure / estimate | Design speed relationship to zoned speed |  |  | Sealed Shoulder | Good condition
- Permit vehicles |  |  | Site measure / estimate | Sight Distance | Deficient | 5 | >1.5 metres | Medium condition
- School buses |  |  | Site measure / estimate | Deficiency in Vertical Geometry |  |  | 0.6-1.5 metres | Poor condition
- Farm equipment |  |  | Site measure / estimate | Deficiency in Horizontal Geometry |  |  | <0.6 metres
- Trucks/ Haulage |  |  | Site measure / estimate | Pavement width
- Other (Specify) _______________ |  |  | Site measure / estimate | Surface condition |  |  | Terrain | Sight Distance
TOTAL | 0 | 0 |  |  |  | 5 | Flat | Compliant
c) Future/ Foreseen | % | No. |  | Unsealed Road Hazard Score |  | 1 | Rolling | Partly Deficient
- Local/ passenger |  |  | Estimate |  |  |  | Mountainous | Deficient
- Permit vehicles |  |  | Estimate
- School buses |  |  | Estimate |  |  |  | Lane numbers
- Farm equipment |  |  | Estimate |  |  |  | Adequate
- Trucks/ Haulage |  |  | Estimate |  |  |  | Not Adequate
- Other (Specify) _______________ |  |  | Estimate
TOTAL | 0 | 0
d) History
a) 5 year crash history |  |  | MRWA database
i) Off road crashes - hit object |  |  | MRWA database
ii) Head on |  |  | MRWA database
iii) Right angle |  |  | MRWA database
iv) Other |  |  | MRWA database
4. OTHER
a) Describe
b) Describe
c) Describe
4. Map location and extent
a) Length
b) Width
c) Shape
Note on G5: Use the combined ADT for the road section being assessed. Where counts are not known estimate the traffic flow.
Note on G6: Select the condition that best describes the offset from the road edge to the hazard (within 3 metres or 3-6 metres) Assess severity: • Slight (minor property damage only, eg. kerb, wire-rope barrier, level slope with no hazards). • Moderate (intermittent hazard likely to cause moderate damage or injury, eg. embankment (in cut), longitudinal bridge or wall, mid-size culvert). • High (likely to cause fatality or serious injury e.g. trees greater than 300 mm diameter, rollover (greater than 4:1 fill), transverse wall.
Note on G7: This factor is based on whether the terrain is mountainous, rolling or level.Select the terrain that best describes the average terrain of the section of road under review.
Note on G8: Where the road geometry is not designed consistent with the posted speed limit or the 85th percentile speed (whichever is the greatest) risk increases. Estimate the design speed of geometric elements and compare to the zoned speed or 85th percentile speed and rate accordingly.
Note on G9: For sight distance at either intersections or midblock. Compliant Sight distance meets AustRoads design guidelines. Partly Deficient Sight distance is 2/3 AustRoads design guidelines recommended sight distance. Deficient Sight distance is 1/3 AustRoads design guidelines recommended sight distance.
Note on G10: Assess thecompliance of geometry to design standards: Fully compliant: Geometry complies fully with Austroads / MRWA design criteria Largely compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a low risk Partly compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a moderate risk
Note on G11: Assess the compliance of geometry to design standards: Fully compliant: Geometry complies fully with Austroads / MRWA design criteria Largely compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a low risk Partly compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a moderate risk
Note on G12: The number of lanes should be consistent with the following: Within 200 metres of an intersection - 1 lane for every 500 vpd. Midblock - 1 lane for every 1000 vpd.
Note on G13: This factor relates to the width of the traffic lane in metres. Enter the corresponding descriptor for the condition.
Note on G14: This factor relates to the width of the sealed shoulder in metres. Enter the corresponding descriptor for the condition.
Note on G15: This factor relates to the condition of the road surface. For a sealed surface, it is considered ‘poor’ if the surface has a smooth, glassy appearance and poor skid resistance, is potholed or has loose material on the surface. If the surface condition varies between good and poor, a medium rating can be chosen. Enter the corresponding rating for the condition.
Note on G23: Use the combined ADT for the road section being assessed. Where counts are not known estimate the traffic flow.
Note on G24: Select the condition that best describes the offset from the road edge to the hazard (within 3 metres or 3-6 metres) Assess severity: • Slight (minor property damage only, eg. kerb, wire-rope barrier, level slope with no hazards). • Moderate (intermittent hazard likely to cause moderate damage or injury, eg. embankment (in cut), longitudinal bridge or wall, mid-size culvert). • High (likely to cause fatality or serious injury e.g. trees greater than 300 mm diameter, rollover (greater than 4:1 fill), transverse wall.
Note on G25: This factor is based on whether the terrain is mountainous, rolling or level.Select the terrain that best describes the average terrain of the section of road under review.
Note on G26: Where the road geometry is not designed consistent with the posted speed limit or the 85th percentile speed (whichever is the greatest) risk increases. Estimate the design speed of geometric elements and compare to the zoned speed or 85th percentile speed and rate accordingly.
Note on G27: For sight distance at either intersections or midblock. Compliant Sight distance meets AustRoads design guidelines. Partly Deficient Sight Distance is 2/3 AustRoads design guidelines recommended sight distance. Deficient Sight Distance is 1/3 AustRoads design guidelines recommended sight distance.
Note on G28: Assess the compliance of geometry to design standards: Fully compliant: Geometry complies fully with Austroads / MRWA design criteria Largely compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a low risk Partly compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a moderate risk
Note on G29: Assess the compliance of geometry to design standards: Fully compliant: Geometry complies fully with Austroads / MRWA design criteria Largely compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a low risk Partly compliant: Geometry has minor deviations from Austroads / MRWA design criteria which pose a moderate risk
Note on G30: This factor relates to the width of the pavement in metres. Enter the corresponding descriptor for the condition.
Note on G31: This factor relates to the condition of the road surface. For an unsealed surface, it is considered ‘poor’ if the surface has a rough, loose appearance, is rutted or corrugated and poor skid resistance due to loose material on the surface. If the surface condition varies between good and poor, a medium rating can be chosen. Enter the corresponding rating for the condition.

## Permit
3. WILL A VEGETATION CLEARING PERMIT BE REQUIRED?
Click on the cells in Column B to select Yes or No |  | NONE
No
VEGETATION TO BE CLEARED AS PART OF ROADWORK | SELECT (DROP LIST) | Yes
1. ALLOWED WITHOUT A CLEARING PERMIT
a) No vegetation to be cleared | No | ENCROACHING VEGETATION
b) To remove encroaching vegetation form road footprint | No | No
c) to remove vegetation in an area has previously been cleared within the previous ten years | No | Yes
d) Removing damaged vegetation (describe below) | No | No
Yes
NOT ALLOWED WITHOUT A CLEARING PERMIT
a) Any vegetation other than that listed above | No | SAFETY
VEGETATION PERMIT REQUIRED? | No | No
Yes
If a Vegetation Permit is not required, proceed to "Final Roadworks Plan" worksheet
If a Vegetation Permit is required, proceed to "Vegetation" worksheet |  | DAMAGED VEGETATION
No
Yes
NOT ALLOWED
No
Yes
Vegetation Permit not required
Vegetation Permit required

## Vegetation
4. DESCRIBE NATURAL ENVIRONMENT |  |  |  | 5.IDENTIFY NEEDS TO CONSERVE VEGETATION
Complete table below to collect information of the adjacent roadside vegetation relevant to the DEC Ten Clearing Principles |  |  |  | Click on the cells in Column H to select the condition of each factor |  |  | Biodiversity | Fauna | History and Heritage
NATURAL ENVIRONMENT | DATA | REFERENCE | Approx. cost | FACTOR | SELECT CONDITION (DROP LIST) | SCORE | World heritage - nationally listed | Threatened fauna | Contains Indigenous artifacts Registered Heritage site
10 CLEARING PRINCIPALS |  |  |  | Biodiversity | 0 species (cleared) | 0 | Nature reserve | Priority 1 fauna | Registered ethnographic site
(a) Biodiversity |  |  |  | Factor 1 - Relative value | Not higher quality | 0 | >250 species | Priority 2 fauna | Contains stored data
Datasets required for base level information on biodiversity |  |  |  | Fauna habitat | No fauna | 0 | >100 species | Priority 3 fauna | Site of European Heritage eg school, building
Declared Rare and Priority Flora |  | DEC data request | $300 + gst | Factor 1 - Corridors | No ecological corridors, stepping stones are present | 0 | > 50 species | Priority 4 fauna | Site of other historical significance
Threatened Ecological Communities |  | DEC data request | $200 + gst | Factor 2 - Breeding habitat | No breeding habitat present for threatened fauna | 0 | < 50 species | Other significant fauna | No significance
Threatened and Priority Fauna |  | DEC data request | $200 + gst | Factor 3 - Isolated population | No local isolated population of fauna present | 0 | 0 species (cleared) | No significant fauna | Amenity and Character
Vegetation type and condition |  | Site survey | Cost will be variable | Flora | No significant flora | 0 | Biodiversity - factor 1 | No fauna | High Visual amenity / beauty
Additional datasets |  |  |  | Factor 1 - Special species | No special species present | 0 | Higher quality than nearby vegetation | Fauna factor 1 | Unusual Landscape Character
aerial imagery |  | Landgate, SLIP, Google Earth, Near Maps | Purchase from Landgate or free to view on Google Earth and Nearmap | Factor 2 - Presence of habitat | No habitat for threatened species present | 0 | Not higher quality | Ecological corridors, stepping stones are present | Local tourist spot
location of World Heritage Areas, National Parks, Nature Reserves and ESAs |  | DEC, SLIP | Free to view on SLIP | Threatened Ecological Community | No TEC, PEC or other significant community within 1 km | 0 | Flora | No ecological corridors, stepping stones are present | No value
total vascular plant taxa (species, subspecies and varieties) inventory |  | DEC Florabase, SLIP | Free to view | Extent of clearing | <80% remaining | 1 | Threatened flora (EPBC or DEC) | Fauna factor 2
vascular plant taxa diversity for each ecological community |  | DEC Florabase, SLIP | Free to view | Factor 1 - Remnant vegetation | Large remnant in otherwise cleared landscape | 5 | Priority 1 flora | Presence of breeding habitat for threatened fauna
total vertebrate and invertebrate fauna taxa (genera, species and subspecies) inventory |  | DEC Nature Map | Free to view | Proximity of Water | Located within wetland buffer | 8 | Priority 2 flora | No breeding habitat present for threatened fauna
number of ecological communities (fauna communities (assemblages)) |  | site survey | Cost will be variable | Effect on land degradation | On a slope >1:10 | 1 | Priority 3 flora | Fauna factor 3
macrohabitat diversity |  | site survey | Cost will be variable | Factor 1 - Soil type | Site is predominently soil type other than sandy soil | 0 | Priority 4 flora | Local isolated population of fauna present
(b) Fauna habitat |  |  |  | Factor 2 - Soil acidity | Soil is non acidic | 0 | Other significant flora | No local isolated population of fauna present
Datasets required for base level information on fauna habitat |  |  |  | Factor 3 - Salinity risk | No salinity risk | 0 | No significant flora | Extent of clearing
protected or threatened fauna, priority fauna or fauna otherwise of significance |  | DEC Threatened species and community database | $200 + gst | Impact on Conservation Area | Not adjacent to reserve | 0 | Flora factor 1 | <1% remaining
EPBC protected matters search tool |  | DSEWPC website report | Staff time | Factor 1 - Corridor | No Corridor | 0 | Special species present | <2% remaining
NatureMap search tool |  | report | Staff time | Impact on Water Quality | On a slope >1:10 | 1 | No special species present | <5% remaining
fauna habitat i.e presence of breeding, sheltering or feeding sites for protected fauna |  | Site survey | Cost will be variable | Factor 1 - Soil type | Site is predominently soil type other than sandy soil | 0 | Flora factor 2 | <10% remaining
Additional datasets |  |  |  | Factor 2 - Soil acidity | Soil is non acidic | 0 | Habitat for threatened species present | <30% remaining
location of Environmentally Sensitive Areas |  | DEC, SLIP | Free to view on SLIP | Factor 3 - Salinity risk | No salinity risk | 0 | No habitat for threatened species present | <50% remaining
corridor of linked vegetation |  | DAFWA, SLIP | Free to view on SLIP | Factor 4 - Nutrients | Not likely to result in nutrient export | 0 | Threatened Ecological Community | <80% remaining
native vegetation extent |  | DAFWA, SLIP | Free to view on SLIP | Factor 5 - ASS | Not in estuarine or swampy area likely to generate acid | 0 | TEC on site | Clearing Factor 1
native vegetation extent by type |  | DAFWA, SLIP | Free to view on SLIP | Impact on flooding | Not affected by flooding, high water table or clay soils | 0 | Environmentally Sensitive Area | Large remnant in otherwise cleared landscape
(c) Flora |  |  |  | History and Heritage | No significance | 0 | TEC within 1 km | Consistent with adjacent landscape
Datasets required for base level information on flora |  |  |  | Amenity and Character | No value | 0 | PEC on site | Land degradation
protected or threatened flora, priority flora or flora otherwise of significance |  | DEC Threatened species and community database | $200 + gst |  |  |  | PEC within 1 km | Slope
EPBC protected matters search tool |  | DSEWPC website report | Staff time | Total | Total | 16 | Other significant community | On a slope >1:3
Additional datasets |  |  |  | Vegetation Value Score |  | 1 | No TEC, PEC or other significant community within 1 km | On a slope >1:6
presence of habitat for protected flora |  | site survey | Cost will be variable |  |  |  | Proximity of water | On a slope >1:10
corridor of linked vegetation |  | DAFWA, SLIP | Free to view on SLIP |  |  | 1 | Containing EP Lake, ESA, Protected, significant or conservation category
native vegetation extent |  | DAFWA, SLIP | Free to view on SLIP |  |  |  | Located within wetland buffer | Soil type
native vegetation extent by type |  | DAFWA, SLIP | Free to view on SLIP |  |  |  | Located in minor wetland or creek | Site is predominently sandy soil
(d) Threatened Ecological Community | [6 empty] | Isolated riverine or wetland trees | Site is predominently soil type other than sandy soil
presence of Threatened Ecological Community (TEC) and Priority Ecological Community (PEC) |  | DEC Threatened species and community database | $200 + gst |  |  |  | No proximity to water | Soil acidity
EPBC protected matters search tool |  | DSEWPC website report | Staff time |  |  |  | Conservation area | Soil pH <4
presence of Environmentally Sensitive Area |  | DEC, SLIP | Free to view on SLIP |  |  |  | Adjacent to National Park or Nature reserve | Soil pH <5
(e) Extent of clearing | [6 empty] | Adjacent to Shire reserve | Soil is non acidic
aerial imagery |  | Landgate, SLIP, Google Earth, Near Maps | Purchase from Landgate or free to view on Google Earth and Nearmap |  |  |  | Adjacent to Land for Wildlife or Conservation Covenant Land | Soil salinity risk
native vegetation extent |  | DAFWA, SLIP | Free to view on SLIP or purchase dataset from DAFWA |  |  |  | Not adjacent to reserve | High salinity risk
CAR database |  | SLIP download | Free |  |  |  | Conservation area factor 1 | Moderate salinity risk
(f) Proximity of Water | [6 empty] | Through sole corridor to conservation area | Low salinity risk
aerial imagery |  | Landgate, SLIP, Google Earth, Near Maps | Purchase from Landgate or free to view on Google Earth and Nearmap |  |  |  | No Corridor | No salinity risk
presence of Environmental Protection Policy or conservation category lake |  | DEC/EPA, SLIP | Free to view on SLIP |  |  |  | Water factor 4
presence of Environmentally Sensitive Area |  | DEC, SLIP | Free to view on SLIP |  |  |  | Likely to result in nutrient export
presence of significant wetland |  | DEC, SLIP | Free to view on SLIP |  |  |  | Not likely to result in nutrient export
RAMSAR wetlands |  | DEC, SLIP | Free to view on SLIP |  |  |  | Water factor 5
presence of rivers and creeks |  | DOW, SLIP | Free to view on SLIP |  |  |  | In estuarine or swampy area likely to generate acid
(g) Effect on land degradation | [6 empty] | Not in estuarine or swampy area likely to generate acid
contours |  | SLIP, Google Pro, Landgate | Free to view from SLIP or purchase from Landgate |  |  |  | Impact on flooding
land use capability |  | DAFWA, NRM, SLIP | Free to view from NRM SLIP |  |  |  | Area or nearby area suffers from flooding
groundwater salinity |  | NRM SLIP | Free to view from NRM SLIP |  |  |  | Water table within 1 m of surface
salinity risk |  | DAFWA, SLIP | Free to view from NRM SLIP |  |  |  | Clay soils
subsurface compaction |  | DAFWA, SLIP | Free to view from NRM SLIP |  |  |  | Not affected by flooding, high water table or clay soils
water erosion |  | DAFWA, SLIP | Free to view from NRM SLIP
subsurface acidification |  | DAFWA, SLIP | Free to view from NRM SLIP
water repellency |  | DAFWA, SLIP | Free to view from NRM SLIP
(h) Impact on Conservation Area
aerial imagery |  | Landgate, SLIP, Google Earth, Near Maps | Purchase from Landgate or free to view on Google Earth and Nearmap
cadastre |  | SLIP | Free to view on SLIP
location of World Heritage Areas, National Parks, Nature Reserves and ESAs |  | DEC, SLIP | Free to view on SLIP
location of DEC managed land |  | DEC, SLIP | Free to view on SLIP
location of Shire Reserves |  | DEC, SLIP | Free to view on SLIP
corridor of linked vegetation |  | DAFWA, SLIP | Free to view on SLIP
Land for Wildlife or Conservation Covenant Land |  | DEC | Free on DEC website
Conservation Covenant Land |  | National Trust of Australia (WA) | Free on National Trust website
Woodland Watch site |  | Florabase | Free to view on Florabase
Bush Forever site |  | SLIP | Free to view on SLIP
(i) Impact on Water Quality
contours |  | SLIP, Google Pro | Free to view on SLIP or purchase from Landgate
Water Information Network (WIN) database of surface water quality |  | DOW, SLIP | Free to view on GDA and SLIP
Water Information Network (WIN) database of ground water quality |  | DOW, SLIP | Free to view on GDA and SLIP
salinity risk |  | DAFWA, SLIP | Free to view on SLIP
water erosion |  | DAFWA, SLIP | Free to view on SLIP
subsurface acidification |  | DAFWA, SLIP | Free to view on SLIP
water repellency |  | DAFWA, SLIP | Free to view on SLIP
phosphorus export risk |  | DAFWA, SLIP | Free to view on SLIP
presence of Acid Sulfate Soils |  | DEC, SLIP | Free to view on SLIP
(j) Impact on flooding
aerial imagery |  | Landgate, SLIP, Google Earth, Near Maps | Purchase from Landgate or free to view on Google Earth and Nearmap
presence of wetlands |  | DEC/EPA, SLIP | Free to view on SLIP
presence of rivers and creeks |  | DOW, SLIP | Free to view on SLIP
flood risk |  | DAFWA, NRM SLIP | Free to view on SLIP
Water Information Network (WIN) database of ground water levels |  | DOW | Free to view on GDA
Floodplain mapping |  | Shire | Free to view on SLIP
water logging |  | NRM SLIP | Free to view on SLIP
soil landscape systems |  | DAFWA, SLIP | Free to view on SLIP
SOCIAL AND HERITAGE FACTORS
a) History and Heritage
Indigenous artefacts Registered Heritage site |  | DIA database | Free to obtain online
Registered ethnographic site |  | DIA database | Free to obtain online
Stored data |  | DIA database | Free to obtain online
Site of European Heritage (eg school, building) |  | Shire, Heritage Council of WA database, Australian Heritage Database (DSEWPC) | Free to obtain online
Site of other historical significance |  | Shire | Staff time
b) Amenity and Character
High Visual amenity / beauty |  | Shire, site survey | Cost will be variable
Unusual Landscape Character |  | Shire, site survey | Cost will be variable
Local tourist spot |  | Shire | Staff time
Note on G5: Fauna Habitat: The value of the vegetation is also dependent on the role it plays in providing fauna habitat. Where threatened fauna is present rate accordingly. Elsewhere assess the class of fauna most likely to be present at the site.
Note on G6: Biodiversity factor: If the vegetation is of higher quality than that adjacent to the site, apply additional weighting.
Note on G7: Fauna Habitat: The value of the vegetation is also dependent on the role it plays in providing fauna habitat. Where threatened fauna is present rate accordingly. Elsewhere assess the class of fauna most likely to be present at the site.
Note on G8: Fauna Factors: If any of the following factors are present apply relevant weighting.
Note on G11: Flora: The importance of vegetation can be measured in part by the presence of threatened or priority flora. Assess if threatened flora is present and rate accordingly. Priority flora are included on a supplementary conservation list called the Priority Flora List and the first three categories cover poorly known species. The categories are arranged in order of priority for undertaking further surveys. The fourth category of priority flora covers species that have been adequately surveyed and are considered to be rare but not currently threatened
Note on G12: Flora Factors: The importance of vegetation is influenced where certain factors are present. If factors are present, rate accordingly.
Note on G14: TEC: Threatened ecological community (TEC) is a term used for ecosystems that are in danger of being lost due to some threatening process. Possible threatened ecological communities that do not meet survey criteria or that are not adequately defined are designated as Priority Ecological Community (PEC) The value of vegetation is in part influenced by the presence of TEC or PEC and is rated accordingly.
Note on G15: Clearing: The greater the extent of clearing that has already occurred, the more important is the value of the remnant vegetation. Assess the extent remaining and rate accordingly.
Note on G16: Clearing Factor: Weighting is to be applied where the vegetation being assessed is largely in an otherwise cleared landscape.
Note on G18: Land Degradation: Where slopes are steep, clearing of vegetation increases the risk of erosion and degradation. The representative slope of the land under review should be estimated and the corresponding rating applied.
Note on G19: Degradation Factors: Degradation of soil can be affected by soil type, pH and salinity. Assess the potential for these factors to be present and rate accordingly.
Note on G24: Water Quality: Vegetation plays an important role in influencing water quality. Where vegetation is cleared the greater the slope the greater the impact in terms of erosino and subsequent siltation of water bodies. Assess the representative slope of the site being assessed adn apply the appropriate rating.
Note on G25: Water Quality Factors: The impact of clearing on water quality is likely to be greater wehr other factors are present. Assess the site and apply the 5 factors accordingly.

## Action Matrix
6. RESOLVE ISSUES WITH ACTION MATRIX
[15 empty] | matrix | Action
[6 empty] | 0 |  |  |  | 0 |  |  |  |  | 11 | I
|  | Calculated Roadwork Value (Sealed) |  |  |  | 0 |  |  |  | 1 |  |  |  |  | 12 | G
[7 empty] | Roadwork Value (R) |  |  | 1 |  |  |  |  | 13 | B
[10 empty] | 10 |  |  |  |  | 14 | A
[7 empty] | Vegetation Value (V) |  |  | 3 |  |  |  |  | 21 | J
[10 empty] | 13 |  |  |  |  | 22 | H
[7 empty] | Domain |  |  | B |  |  |  |  | 23 | B
[15 empty] | 24 | A
Click on the filter list of the chosen Domain to select the list of actions | [14 empty] | 31 | K
Click on cells in Column O to state whether action is feasable or not and explain why in Column P | [14 empty] | 32 | F
A | B | C | D | E | F | G | H | I | J | K | CATEGORY | ACTION | FEASABLE? | COMMENT | 33 | E
A | B | C | D | E |  | G | H | I |  |  | 1. Reduce likelihood of vehicle leaving road and severity of crash | a) Reduce speed limits to reduce the risk of errant driving or the impact of any collision with roadside hazards |  |  | 34 | C | Yes | 1
A | B | C | D | E | F | G | H |  | J |  | 2. Reduce likelihood of vehicle leaving road by improving road/ infrastructure | a) Improve quality of pavement and edges/shoulders |  |  | 41 | K | No
A | B | C | D | E | F | G | H |  |  |  |  | b) Install (more) guideposts (reflective delineation) |  |  | 42 | K | Yes | 2
A | B | C | D | E | F | G | H |  |  |  |  | c) Install guideposts (reflective delineation) adjacent to trees |  |  | 43 | F | No
A | B | C | D | E | F | G | H |  |  |  |  | d) Reinstate/apply edge lines and centre lines |  |  | 44 | D | Yes | 3
A | B | C | D | E | F | G | H |  |  |  |  | e) Install audible / tactile edge line |  |  |  |  | No
A | B | C | D | E | F | G | H |  |  |  |  | f) Widen or extend the seal to include the shoulder of the road |  |  |  |  | Yes | 4
A A A A A A: A; B B B B B B: B; C C C C C C: C |  |  |  |  | g) Put up signs warning of trees close to road |  |  |  |  | No
D D D D D D: D; E E E E E E: E; F F F F F F: F |  |  |  | 3. Reduce severity of clearing and risk of crash | a) Install safety barriers along verge on stretches of road or around individual trees located close to the travelling lane |  |  |  |  | Yes | 5
A | B | C | D | E |  | G | H |  |  |  | 4. Reduce likelihood and severity of clearing by changing table drain design | a) Realign table drains around trees where possible |  |  |  |  | No
A | B | C | D | E |  | G | H |  |  |  |  | b) Use excavators to create table drains rather than graders |  |  |  |  | Yes | 6
A | B | C | D | E |  | G | H |  |  |  |  | c) Construct drainage offshoots instead of widening table drains |  |  |  |  | No
A A A A A A: A; B B B B B B: B; D D D D D D: D; G G G G G G: G |  |  |  |  | d) Increase table drain batter slopes from 1:4 (recoverable) to 1:3 (traversable) to decrease width (both fore slope and back slope) |  |  |  |  | Yes | 7
A A A A A A: A; D D D D D D: D; G G G G G G: G |  |  |  |  | e) Reduce table drain width, depth and flatten slopes |  |  |  |  | No
A A A A A A: A; D D D D D D: D; G G G G G G: G |  |  |  |  | f) Eliminate table drain |  |  |  |  | Yes | 8
[12 empty] | g) Retain frangible vegetation on backslopes |  |  |  |  | No | bar: A A A A A A; D D D D D D
A A A A A A: A; D D D D D D: D; H H H H H H: H |  |  |  | 5. Reduce severity of clearing through selective clearing | a) Prune trees at edge of formation, both horizontally (eg overhanging branches) and vertically (eg encroaching branches) |  |  |  |  | Yes | 9
A A A A A A: A; B B B B B B: B; D D D D D D: D |  |  |  |  | b) Reduce recovery zone widths (eg retain trees >2 m from edge of road) |  |  |  |  | No
A | B | C | D |  |  | G | [5 empty] | c) Clear only at intersections / driveways |  |  |  |  | Yes | 10
A | B | C | D |  |  | G | [5 empty] | d) Clear only at bends |  |  |  |  | No
A | B |  | D |  |  | G | H |  |  |  |  | e) Review the longitudinal profile of the road to reduce cut / fill requirements |  |  |  |  | Yes | 11
A | B | C | D |  |  | G | H |  |  |  |  | f) Construct passing pockets |  |  |  |  | No
D D D D D D: D; E E E E E E: E; F F F F F F: F; H H H H H H: H | I | J | K |  | g) Remove trees only while leaving the understorey (ie retain frangible vegetation) |  |  |  |  | Yes | 12
D D D D D D: D; E E E E E E: E; F F F F F F: F; H H H H H H: H | I | J | K | 6. Reduce likelihood and severity of clearing and risk of crash by realligning road | a) Realign road by clearing on one side of the existing transport corridor, the side with the overall poorest quality vegetation |  |  |  |  | No
C C C C C C: C; D D D D D D: D; E E E E E E: E; F F F F F F: F |  |  |  |  | b) Avoid clearing an unmade road reserve adjacent to an approved subdivision in an already cleared area |  |  |  |  | Yes | 13
C C C C C C: C; D D D D D D: D; E E E E E E: E; F F F F F F: F |  |  |  |  | c) Construct some or all of the road, or construct a new lane, in a cleared area such as a paddock |  |  |  |  | No
C C C C C C: C; D D D D D D: D; E E E E E E: E; F F F F F F: F |  |  |  |  | d) Consider other alternative alignments |  |  |  |  | Yes | 14
[8 empty] | I | J | K | 7. Reduce risk and severity of crash | a) Clear whole alignment |  |  |  |  | No
[11 empty] | Extra options to consider | [5 empty] | Yes | 15
[11 empty] | 8. Potential options | a) Construct the road using pervious pavement to avoid or reduce the need for additional clearing for drainage infrastructure |  |  |  |  | No
[12 empty] | b) Install median |  |  |  |  | Yes | 16
[12 empty] | c) Install wire rope barrier in median |  |  |  |  | No
[17 empty] | Yes | 17
No
[17 empty] | Yes | 18
No
[17 empty] | Yes | 19
No
[17 empty] | Yes20 | 20
No
[17 empty] | Yes | 21
No
[17 empty] | Yes | 22
No
[17 empty] | Yes | 23
No
[17 empty] | Yes | 24
No
[17 empty] | Yes | 24
No
[17 empty] | Yes | 25
No
[17 empty] | Yes | 26
No
[17 empty] | Yes | 27
No
[17 empty] | Yes | 28
No
[17 empty] | Yes | 29
No
[17 empty] | Yes | 30
No
[17 empty] | Yes | 31
No

## Final Roadworks Plan
7. DEVELOP FINAL ROAD WORKS PLAN
ITEM | DESCRIPTION
1. REASON FOR ROAD WORKS
a) Traffic
i) Larger/ heavy vehicles
ii) Increased traffic volume
iii) Haulage Route (eg CBH)
iv) Special (eg school Bus)
b) Safety
i) Line of Sight
ii) Prevent collison of vegetation
iii) Prevent collision with infrastructure
iv) Poor road surface
v) T to Y junctions
vi) Overtaking
vii) Weather
c) Access
i) Local use
ii) Tourism
iii) Private/ Business
iv) Government
d) Other
i) Gravel Pit
ii) Limestone Pit
2. ROAD WORK TYPE
a) Upgrade
i) Road widening
ii) Road sealing
iii) Road seal widening
b) Floodways
i)
ii)
c) New Roads
i) Unsealed
ii) Sealed
d) Other
i) Gravel Pits
ii) Limestone Pit
3. VEGETATION TO BE CONSERVED
a) Significant Vegetation types and reasons
b) Location and extent
4. ROADWORK FEATURES
a) Delineation
i) Line marking
ii) Sight Distance
b) Design
i) Rumble Strips
ii) Shoulder clearing
iii) Move obstacles
iv) Safety barriers
v) Roadside Slope
vi) Drainage structure
c) Speed Management
i) Speed limit
ii) Signage
5. MAP LOCATIONS AND EXTENT of ROAD WORKS
a) Length
b) Width
c) Shape